## W1
PROJECT REPORT
Group | Delivery Food
Week | 05/01/2025 - 12/01/2025
I. Status Report
# | Project Task | In-charge | Status | Notes (Work Item in Details)
| Complete Project Plan | All Team | Completed
II. Project Issues
# | Project Issue | Owner | Status | Notes (Solution, Suggestion, etc.)
III. Next Week Plan
# | Project Work Item | In-charge | Deadline | Notes (Task Details, etc.)
| Create SRS | All Team | 14/01/2025
IV. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Date | Notes

## W2
PROJECT REPORT
Group | Delivery Food
Week | 12/01/2025 - 19/01/2025
I. Status Report
# | Project Task | In-charge | Status | Notes (Work Item in Details)
1 | Create SRS | All Team | Completed
II. Project Issues
# | Project Issue | Owner | Status | Notes (Solution, Suggestion, etc.)
III. Next Week Plan
# | Project Work Item | In-charge | Deadline | Notes (Task Details, etc.)
1 | Define Database Schema | Nam | 26/01/2025 | Use MySQL or SQLServer
2 | Define layout for Delivery Food | Nam | 26/01/2025
IV. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Date | Notes

## W3
PROJECT REPORT
Group | Delivery Food
Week | 03/02/2025 - 09/02/2025
I. Status Report
# | Project Task | In-charge | Status | Notes (Work Item in Details)
1 | Define Database Schema | All Team | Completed | Use Sql Server
2 | Define layout for Delivery Food | All Team | Completed
II. Project Issues
# | Project Issue | Owner | Status | Notes (Solution, Suggestion, etc.)
III. Next Week Plan
# | Project Work Item | In-charge | Deadline | Notes (Task Details, etc.)
1 | Coding - Authentication/Authorize | Nam | 15/02/2025
2 | Create Blackbox Testcase | All Team | 2025-10-02
3 | Review and update Blackbox Testcase | All Team | 2025-11-02
IV. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Date | Notes