## Team 1
Date | Duration (h) | Timeframe | Topic | Status
2015-08-04 | 8 | 08:00-17:30 | Mock Project - Day 1 - Kick off + Create requirement outline | Started
2015-08-06 | 8 | 08:00-17:30 | Mock Project - Day 2 - Create SRS
2015-08-07 | 8 | 08:00-17:30 | Mock Project - Day 3 - Review and update SRS
2015-08-10 | 8 | 08:00-17:30 | Mock Project - Day 4 - Database Design + Review Database Design
2015-08-11 | 8 | 08:00-17:30 | Mock Project - Day 5 - Create Blackbox Testcase
2015-08-12 | 8 | 08:00-17:30 | Mock Project - Day 6 - Review and update Blackbox TC
2015-08-13 | 8 | 08:00-17:30 | Mock Project - Day 7 - Coding
2015-08-14 | 8 | 08:00-17:30 | Mock Project - Day 8 - Coding
2015-08-17 | 8 | 08:00-17:30 | Mock Project - Day 9 - Coding
2015-08-18 | 8 | 08:00-17:30 | Mock Project - Day 10 - Coding
2015-08-19 | 8 | 08:00-17:30 | Mock Project - Day 11 - Review code + UT
2015-08-20 | 8 | 08:00-17:30 | Mock Project - Day 12 - UT
2015-08-21 | 8 | 08:00-17:30 | Mock Project - Day 13 - IT
2015-08-24 | 8 | 08:00-17:30 | Mock Project - Day 14 - IT + Create Test Report
2015-08-25 | 8 | 08:00-17:30 | Mock Project - Day 15 - Final Report
2015-08-26 | 8 | 08:00-17:30 | Mock Project - Day 16 - Final Report (cont)
2015-08-27 | 8 | 08:00-17:30 | Sum-up and Closing Ceremony
2015-08-28 | 2 | 08:00-10:00 | Class Meeting 3
2015-08-28 | 2 | 10:00-12:00 | TOEIC Test 2
2015-08-28 | 4 | 13:30-17:30 | Re-test session 2 (For ASQL, ATXB)
Tên đề tài: | Hệ thống giao thức ăn nhanh
Nguyễn Lê Hoài Nam (Leader)
Lê Ngọc Nhất Huy
Nguyễn Lê Uyên
Lê Thị Vân Anh
Từ Nguyễn Minh Tiên
Formulas:
Date = IF(WEEKDAY([Date, row above])=6,[Date, row above]+ 3,[Date, row above]+ 1)+1
Date = IF(WEEKDAY([Date, row above])=6,[Date, row above]+ 3,[Date, row above]+ 1)