## Team 1
Date | Duration (h) | Timeframe | Topic | Status | Member
2025-01-11 | 12 | 10:00-22:00 | Mock Project - Kick off + Create requirement outline + Project Plan | Done | All
2025-01-14 | 12 | 10:00-22:00 | Mock Project - Create SRS | Done | All
2025-01-17 | 12 | 10:00-22:00 | Mock Project - Review and update SRS | Pending | Nam
2025-01-22 | 12 | 10:00-22:00 | Mock Project - Database Design + Review Database Design |  | All
2025-02-05 | 12 | 10:00-22:00 | Mock Project - Create Blackbox Testcase |  | All
2025-02-06 | 12 | 10:00-22:00 | Mock Project - Review and update Blackbox TC |  | All
2025-02-07 | 12 | 10:00-22:00 | Coding - Authentication/Authorize |  | Nam
| 12 | 10:00-22:00 | CRUD Product, CRUD Category |  | Uyên
|  | 10:00-22:00 | View Profile, Edit Profile |  | Anh
|  | 10:00-22:00 | View Menu, Add to Cart, Note Product |  | Huy
|  | 10:00-22:00 | Search and Filter Product, Send and view feedback Product |  | Tiên
2025-02-20 | 12 | 10:00-22:00 | Payment |  | Huy
|  |  | View Order Status, View feedback (contact) |  | Uyên
|  |  | View Order History, Ban/Unban Account |  | Anh
|  |  | View, Add to Favorite List |  | Tiên
2025-03-01 | 12 | 10:00-22:00 | View revenue |  | Nam
|  |  | Print invoice |  | Nam
2025-03-11 | 12 | 10:00-22:00 | Mock Project - Review code + UT |  | All
2025-03-15 | 12 | 10:00-22:00 | Mock Project - UT |  | All
2025-03-18 | 12 | 10:00-22:00 | Mock Project - IT |  | All
2025-03-22 | 12 | 10:00-22:00 | Mock Project - IT + Create Test Report |  | All
2025-03-29 | 12 | 10:00-22:00 | Mock Project - Final Report
2025-03-30 | 12 | 10:00-22:00 | Mock Project - Final Report (cont)
Tên đề tài: | Hệ thống giao thức ăn nhanh
Nguyễn Lê Hoài Nam (Leader)
Lê Ngọc Nhất Huy
Nguyễn Lê Uyên
Lê Thị Vân Anh
Từ Nguyễn Minh Tiên