## W1
PROJECT REPORT
Group | Delivery Food
Week | 05/01/2025 - 12/01/2025
I. Status Report
# | Project Task | In-charge | Status | Notes (Work Item in Details)
| Complete Project Plan | All Team | Completed
II. Project Issues
# | Project Issue | Owner | Status | Notes (Solution, Suggestion, etc.)
III. Next Week Plan
# | Project Work Item | In-charge | Deadline | Notes (Task Details, etc.)
| Create SRS | All Team | 14/01/2025
IV. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Date | Notes

## W2
PROJECT REPORT
Group | Delivery Food
Week | 12/01/2025 - 19/01/2025
I. Status Report
# | Project Task | In-charge | Status | Notes (Work Item in Details)
1 | Create SRS | All Team | Completed
II. Project Issues
# | Project Issue | Owner | Status | Notes (Solution, Suggestion, etc.)
III. Next Week Plan
# | Project Work Item | In-charge | Deadline | Notes (Task Details, etc.)
1 | Define Database Schema | Nam | 26/01/2025 | Use MySQL or SQLServer
2 | Define layout for Delivery Food | Nam | 26/01/2025
IV. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Date | Notes

## W3
PROJECT REPORT
Group | Delivery Food
Week | 03/02/2025 - 09/02/2025
I. Status Report
# | Project Task | In-charge | Status | Notes (Work Item in Details)
1 | Define Database Schema | All Team | Completed | Use Sql Server
2 | Define layout for Delivery Food | All Team | Completed
II. Project Issues
# | Project Issue | Owner | Status | Notes (Solution, Suggestion, etc.)
III. Next Week Plan
# | Project Work Item | In-charge | Deadline | Notes (Task Details, etc.)
1 | Coding - Authentication/Authorize | Nam | 15/02/2025
2 | Create Blackbox Testcase | All Team | 2025-10-02
3 | Review and update Blackbox Testcase | All Team | 2025-11-02
IV. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Date | Notes

## W4
PROJECT REPORT
Group | Delivery Food
Week | 10/02/2025 - 16/02/2025
I. Status Report
# | Project Task | In-charge | Status | Notes (Work Item in Details)
1 | Coding - Authentication/Authorize | Nam | Completed
2 | Create Blackbox Testcase | All Team | Completed
2 | Review and update Blackbox Testcase | All Team | Completed
II. Project Issues
# | Project Issue | Owner | Status | Notes (Solution, Suggestion, etc.)
III. Next Week Plan
# | Project Work Item | In-charge | Deadline | Notes (Task Details, etc.)
1 | Coding- CRUD Product,CRUD Category | Uyen | 25/02/2025
2 | Coding- View Profile, Edit Profile | Anh | 25/02/2025
3 | Coding - View Menu, Add to Cart, Note Product | Huy | 25/02/2025
4 | Coding - Search and Filter Product, Send and view feedback Product | Tien | 25/02/2025
5 | Review code | Nam | 26/02/2025
IV. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Date | Notes

## W5
PROJECT REPORT
Group | Delivery Food
Week | 17/02/2025 - 23/02/2025
I. Status Report
# | Project Task | In-charge | Status | Notes (Work Item in Details)
1 | Coding- CRUD Product,CRUD Category | Uyen | Completed
2 | Coding- View Profile, Edit Profile | Anh | Completed
3 | Coding - View Menu, Add to Cart, Note Product | Tien | Completed
4 | Coding - Search and Filter Product, Send and view feedback Product | Huy | Completed
5 | Review code | Nam | Completed
II. Project Issues
# | Project Issue | Owner | Status | Notes (Solution, Suggestion, etc.)
III. Next Week Plan
# | Project Work Item | In-charge | Deadline | Notes (Task Details, etc.)
1 | Payment | Uyen | 2025-03-03
2 | View Order Status, View Feedback | Anh | 2025-03-03
3 | View Order History, Ban/Unban Account | Huy | 2025-03-03
4 | View revenue, Filter revenue by date | Nam | 2025-03-03
5 | View, Add to Favorite List | Tien | 2025-03-03
IV. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Date | Notes